Create a Project Schedule in this worksheet.
Enter title of this project in cell B1.
Information on how to use this worksheet, including instructions for screen readers and the author of this workbook, is in the About worksheet.
Phase 3's sample block starts in cell B20.
This row marks the end of the Project Schedule. DO NOT enter anything in this row.
Insert new rows ABOVE this one to continue building out your Project Schedule.
Changing this number will scroll the Gantt Chart view.
Enter Company name in cel B2.
Enter the name of the Project Lead in cell C3. Enter the Project Start date in cell Q1. Project Start: label is in cell I1.
The Display week in cell Q2 is the starting week to display in the project schedule in cell I4. The project start date is Week 1. To change the display week, enter a new week number in cell Q2.

Start date for each week is auto calculated starting in I4.
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date and are auto calculated.

Today's date is outlined from today's date in row 5 through the entire date column to the end of the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new title in cell B8.
To delete the phase and work only from tasks, simply delete this row.
B9 contains the task name. C9 is the assignee. D9 is a progress bar that shades based on the number entered into the cell.

E9 contains the start date and F9 contains the end date.

The Gantt chart will fill in starting in cell I9 based on task dates.
Rows 10 through 13 repeat the pattern from row 9.

Repeat the instructions from cell A9 for all task rows in this worksheet.

Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more.
Cell B14 contains the Phase 2 sample title. Enter a new title in cell B14.
To delete the phase and work only from tasks, simply delete this row. To remove the phase, simply delete the row. Add tasks to previous phase by entering a new row above this one.
## Project_schedule
	IN2033 Project					Project start:					26/01/2026
	MediFlow Solutions		Project lead: Furqan					Display week:					7

				Mar 9, 2026					Mar 16, 2026					Mar 23, 2026					Mar 30, 2026					Apr 6, 2026					Apr 13, 2026					Apr 20, 2026					Apr 27, 2026
	TASK	ASSIGNED TO	PROGRESS	START	END			9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	1	2	3
				M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S	M	T	W	T	F	S	S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.					#NAME?
	Initiation					#NAME?
	Team Name and Logo	Dawud	100%	02/02/2026	02/02/2026		#NAME?
	Set-up Project Binder	Team	100%	26/01/2026	08/02/2026		#NAME?
	Customer Interview	Furqan, Bahja	100%	03/02/2026	03/02/2026		#NAME?
	Deliverable 1			Week 1	Week 5		#NAME?
	Use-case Diagram	Furqan, Haris, James, Bahja	100%	05/02/2026	20/02/2026		#NAME?
	Volere Templates	Bahja, Haris, Huzefa	100%				#NAME?
	Use-case Specification	Dawud, Bahja, Haris	100%	05/02/2026	12/02/2026		#NAME?
	Prioritised List of / Use Cases	Dawud, Furqan, Bahja	100%				#NAME?
	Anticipated Evolution of / system requirements	Faisal, Huzefa	100%				#NAME?
	High-level Design (component diagram)	Furqan, James	100%
	Class diagram of our subsystem	Huzefa, Faisal	100%
	Generated source code with comments	Haris, Bahja	100%	25/02/2026	29/02/2026
	Test cases	James	100%
	Expected Hardware	Furqan	100%
	Deliverable 2			Week 7	Week 13		#NAME?
	Research		100%	09/03/2026	13/03/2026		#NAME?
	GUI Implementation	Dawud, James, Haris, Furqan, Faisal	100%				#NAME?
	Test Implementation	Furqan, Bahja, Huzefa, Dawud, Haris	100%				#NAME?
	IPOS-PU-COMMS			09/03/2026	19/04/2026		#NAME?
	Accept SMTP requests	James					#NAME?
	Accept payment requests	James
	Make SMTP requests	Furqan, Faisal
	Make Stripe requests	Furqan, Faisal
	IPOS-PU-GUI			09/03/2026	19/04/2026
	Commercial form	Furqan	100%
	Non-commercial form	Furqan	100%
	Login screen	Furqan	100%
	Navbar	Furqan	100%
	Merchant profile	Furqan
	Product list	Furqan	100%
	Basket screen	Furqan	100%
	Payment confirm screen	Furqan	100%
	Admin dashboard	Furqan	100%
	Report menu	Furqan	100%
	Registration screen	Furqan	100%
	Promotion feed	Furqan	100%
	IPOS-PU-MEMBERS			09/03/2026	19/04/2026
	Commercial form	Bahja	100%
	Non-commercial form	Bahja	100%
	Process commercial applications	Bahja
	Process non-commercial applications	Bahja
	User details database	Bahja	100%
	Customer authentication	Bahja	100%
	Change password	Bahja
	Prompt password change	Bahja	100%
	Logout	Bahja
	Login	Bahja	100%
	IPOS-PU-PRM			09/03/2026	19/04/2026
	Promotion database	Huzefa
	Make promotion	Huzefa
	Cancel promotion	Huzefa
	Admin account	Huzefa
	Record clicks/sales	Huzefa
	IPOS-PU-RPT			09/03/2026	19/04/2026
	Sales within a period	Faisal
	Ad campaign for a period	Faisal
	Hits of ad campaign	Faisal
	IPOS-PU-SALES			09/03/2026	19/04/2026
	Filter catalogue	Haris	100%	01/04/2026	06/04/2026
	Add to cart	Haris	100%	20/03/2026	23/03/2026
	Confirm order	Haris, Dawud	100%
	Checkout	Haris, Dawud	100%
	Update order status	Haris, Dawud
	Check item for promotion	Haris, Dawud		26/03/2026	19/04/2026
	Record items sold	Haris	100%	02/04/2026	06/04/2026
	Record items viewed	Haris	100%	02/04/2026	06/04/2026
	Calculate tax	Haris, Dawud	100%	20/03/2026	15/04/2026
	Update cart	Haris	100%	20/03/2026	23/03/2026
	Check 10th purchase discount	Haris, Dawud	100%	26/03/2026	19/04/2026
	Check promotion discount	Haris, Dawud	100%	26/03/2026	19/04/2026
	Make purchase	Haris, Dawud	100%
	View cart	Haris	100%	20/03/2026	23/03/2026
	View item	Haris	100%	01/04/2026	06/04/2026
	Search catalogue	Haris	100%	01/04/2026	06/04/2026
	View catalogue	Haris	100%	01/04/2026	06/04/2026
	IPOS-PU-TEST			09/03/2026	19/04/2026
	REST API tests	James
	IPOS-PU-DOCS			09/03/2026	26/04/2026
	Implementation Report	Haris, Huzefa, Bahja, Faisal
	Project Binder	Team	50%	20/04/2026	26/04/2026
				#NAME?
	Insert new rows ABOVE this one					#NAME?